## Readme - how to use
How to use this workbook
Welcome to the Quantitative Improvement tracking and reporting spreadsheet. This provides a simple and consistent way for a team to see their long-term results as they improve themselves.
Assumptions: your team uses a recurring, regularly-scheduled demo for product work. Your team will do the same for sustainability work. Your planning may be iterative or continuous-form, but demos happen on a cadence.
When you start
Update the settings tab with correct values for your team.
Familiarize yourself with the terms and cycle structure. There are comments on various headers (especially on the data table) to help you out.
Familiarize yourself with this workbook. If you do iterative planning, planning & scheduling happens on the Plan sheet. Tracking / data entry will happen on the Data sheet. Reporting / results are split between the Dashboard (visualizations that help you course-correct based on current data) and Historical trends (visualizations that help you see how the team has changed over time).
Especially note the special note about bugs. Bugs are always blue work, and are always additional added items (not planned work). This is true whether they were triaged (delayed until future planning) or not.
Set up any recurring meetings, such as the sustainability planning and demo sessions.
Each sustainability cycle
Right before planning meeting: determine your available capacity (see plannning sheet). This is based on your budget - the spending ratio between product and sustainability stories.
At end of planning meeting: update the data sheet with the number of planned improvements and experiments (just the number of cards).
Right before demo: update the data sheet with the actuals for both experiments and improvements (planned done, additional done, and had desired results). Again, each is the number of cards.
Each product sprint
At end of planning meeting: update the data sheet with the number of planned improvements and experiments (just the number of cards).
Right before demo: update the data sheet with the actuals for both experiments and improvements (planned done, additional done, and had desired results). Again, each is the number of cards.

## Dashboard
Sustain percentage goal | Chart with actuals over recent time
as small table with date and goal
Actual % implemented, for each of the 4 colors on one chart
Actual % with impact, for the two improvement colors, with control band
Target number of experiment options to run | Actual % with impact, for the two experiment colors, with control band
Current percentage of work going to planned work, per color

## Historical trends
Actual total work done, for each color, showing planned and total
CFD with short- and long- term plan work, improvements only

## Data
Product Improvements | Date | Taken into Immediate Future Plan | Added Additional | Removed Planned | Planned done | Additional done | Remaining Planned | Had expected impact | Product Experiments | Date | Taken into Immediate Future Plan | Added Additional | Removed | Planned done | Additional done | Carried Over | Had expected impact | Sustainability Improvements | Date | Taken into Immediate Future Plan | Added Additional | Removed | Planned done | Additional done | Carried Over | Had expected impact | Sustainability Experiments | Date | Taken into Immediate Future Plan | Added Additional | Removed | Planned done | Additional done | Carried Over | Had expected impact
Note on A1: Author: All columns except Date are story card counts. Blue work items are product work improvements. This means they relate to any aspect of the business's product and we have evidence that they implement the right solution to an important problem. Their purpose is to realize value, turning our knowledge of the customer into product advantage.
Note on C1: Author: Cards added to the near-future plan, such as the sprint commitment or the ready for work queue. These represent the planned objectives, either strategic or tactical.
Note on D1: Author: Cards added to work that bypassed the planning cycle, such as during-sprint adds to the sprint or urgent work that bypasses the ready queue and takes the urgent item swimlane. Special note: bugs should always be added additional work, even if they are later removed or were known at the sprint start. Bugs are never planned work, even if they were triaged and scheduled. Bugs are also always product improvements (blue work). A bug fix is never an experiment (you know the value), and it is never a sustainability item (an action taken to prevent a certain category of bug from ever happening again would be a sustainability item). Your team needs to agree about what a bug means. But think of it in terms of measurability. A bug means that a story or part of a story, while bellieved to be done, was done in such a way that the measures of impact don't actually assess the worth of the idea - something gets in the way and changes user behavior. This means that the team has to do additional work in order for the system to actually measure impact of the stories in question. These represent additional work the team has to do that do not further its plan, such as bug fixes, emergencies, special projects, or overhead.
Note on E1: Author: Work items that are removed from the plan without being done. These aren't just delayed until later. Instead, the team decides to not do them. They are no longer intended to be part of the product. Note: all items here are planned work only. Don't record additional adds that were removed without being done. Just take those out of the added additional as if they were never there. If you did partial progress on an added work item and then dropped the rest, consider it as completed additional work. They represent places where the team has gained information that allowed them to realize some work would not be worth doing, and then make the choice to not do that work.
Note on F1: Author: Completed work items that were planned (as in, showed up in the added to plan column at some point in the past and were never removed). These represent progress towards the planned objectives for the product.
Note on G1: Author: Completed work items that bypassed the plan. These represent effort expended that did not accrue to the planned objectives.
Note on H1: Author: Work items that were neither completed nor removed. It will be carried over into the future, into the backlog for future plans. Note: the work should balance for any period. The amount of work taken into the immediate-term plan - (done + removed from plan + remaining) should be zero. Use this to check that you didn't miss anything. This represents work that is not yet done, but we intend to do some day.
Note on I1: Author: Stories that were not only completed, but had the expected impact. This is not about acceptance criteria. Acceptance criteria tell you when a story is done: those allow a story to be added to the done columns. This is about impact criteria: how did the story impact the customer behavior? Frequently we will do good work that does what we intend, but it will have different custommer impacts than we had hoped. This column represents stories that had the measurable impact that we had hoped for. This represents actual value accrual for the company. The story materially changed the company's revenue or revenue-leading measures.
Note on J1: Author: All columns except Date are story card counts. Green work items are product work experiments. This means they relate to any aspect of the business's product and we know what problem they are trying to solve, but don't have evidence yet what solution will best address that problem. Their purpose is to try out a potential solution and gain information about what works.
Note on L1: Author: Cards added to the near-future plan, such as the sprint commitment or the ready for work queue. These represent the planned objectives, either strategic or tactical.
Note on S1: Author: All columns except Date are story card counts. Purple work items are sustainabillity work improvements. This means they relate to any aspect of improving your capacity to do business and we have evidence that they implement the right solution to an important problem. Their purpose is to realize a process or habit change, turning our knowledge of the system into a business advantage.
Note on U1: Author: Cards added to the near-future plan, such as the sprint commitment or the ready for work queue. These represent the planned objectives, either strategic or tactical.
Note on AB1: Author: All columns except Date are story card counts. Orange work items are sustainability work experiments. This means they relate to any aspect of the team's capacity to do business and we know what problem they are trying to solve, but don't have evidence yet what solution will best address that problem. Their purpose is to try out a potential solution and gain information about what works.
Note on AD1: Author: Cards added to the near-future plan, such as the sprint commitment or the ready for work queue. These represent the planned objectives, either strategic or tactical.