## Readme - how to use
How to use this workbook
Welcome to the Quantitative Improvement tracking and reporting spreadsheet. This provides a simple and consistent way for a team to see their long-term results as they improve themselves.
Assumptions: your team uses a recurring, regularly-scheduled demo for product work. Your team will do the same for sustainability work. Your planning may be iterative or continuous-form, but demos happen on a cadence.
When you start
Update the settings tab with correct values for your team.
Familiarize yourself with the terms and cycle structure. There are comments on various headers (especially on the data table) to help you out.
Familiarize yourself with this workbook. If you do iterative planning, planning & scheduling happens on the Plan sheet. Tracking / data entry will happen on the Data sheet. Reporting / results are split between the Dashboard (visualizations that help you course-correct based on current data) and Historical trends (visualizations that help you see how the team has changed over time).
Set up any recurring meetings, such as the sustainability planning and demo sessions.
Each sustainability cycle
Right before planning meeting: determine your available capacity (see plannning sheet). This is based on your budget - the spending ratio between product and sustainability stories.
At end of planning meeting: update the data sheet with the number of planned improvements and experiments (just the number of cards).
Right before demo: update the data sheet with the actuals for both experiments and improvements (planned done, additional done, and had desired results). Again, each is the number of cards.
Each product sprint
At end of planning meeting: update the data sheet with the number of planned improvements and experiments (just the number of cards).
Right before demo: update the data sheet with the actuals for both experiments and improvements (planned done, additional done, and had desired results). Again, each is the number of cards.

## Settings
This team uses regularly-scheduled, recurring planning meetings: | TRUE
If so, number of workdays between demo and the next plan | 0
First product demo date | 2016-06-01
Product demo cycle length (in workdays) | 5
First sustainability demo date | 2016-06-01
Sustainability demo cycle length (in workdays) | 2